## Resources
Resource | Speciality | Notes | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | Hours | Effort Needs | List Price | Adjusted Rate | Total Fees | Cost | Total Cost | Billable
MONTH |  |  | 1 | 2 | 3 | 4 | 5
PHASE
MILESTONE |  |  | PO Issue, 15/04/2026, Invoicing, SGD 34750.00 | P1-Design complete, 01/05/2026, Invoicing, SGD 13900.00 | P1- Basic modules complete, 01/06/2026, Invoicing, SGD 27800.00 | P1- Acceptance complete, 01/07/2026, Invoicing, SGD 20850.00 | P2- Acceptance complete, 16/08/2026, Invoicing, SGD 13900.00
|  |  | m1-rev, 30/04/2026, Revenue, SGD 34750.00 | m2-rev, 31/05/2026, Revenue, SGD 13900.00 | m3-rev, 30/06/2026, Revenue, SGD 27800.00 | P2-Integrations complete, 31/07/2026, Invoicing, SGD 27800.00 | m5-rev, 31/08/2026, Revenue, SGD 13900.00
m4-rev, 31/07/2026, Revenue, SGD 48650.00
EFFORT NEEDS PER PHASE
HOURS PER PHASE
TOTAL HOURS PER MONTH |  |  | 240 | 652 | 788 | 380 | 372 | 2432 |  |  |  | 198114.24 |  | 94913.92
Customer Proj/Prgm Mgr - Sr. Consultant (Singapore) |  | Local PM (Joseph) | 40 | 20 | 20 | 20 | 20 | 120 | 0 | 253 | 253 | 30360 | 125 | 15000 | Yes
Info Systems Architect - Sr. Consultant (GDC India) |  | GDC SA | 80 | 80 | 80 | 40 | 40 | 320 | 0 | 63.4528 | 63.45 | 20304 | 31.73 | 10153.6 | Yes
Technology Consultant - Consultant (Singapore) |  | INT1 GDC TC (Trishten) | 40 | 160 | 160 | 0 | 0 | 360 | 0 | 186 | 186 | 66960 | 82 | 29520 | Yes
Technology Consultant - Sr. Consultant (GDC India) |  | SPE1 | 80 | 160 | 168 | 0 | 0 | 408 | 0 | 63.4528 | 63.45 | 25887.6 | 31.73 | 12945.84 | Yes
Technology Consultant - Sr. Consultant (GDC India) |  | SPE2 | 0 | 0 | 40 | 160 | 160 | 360 | 0 | 63.4528 | 63.45 | 22842 | 31.73 | 11422.8 | Yes
Technology Consultant - Consultant (GDC India) |  | INT2 | 0 | 0 | 0 | 160 | 152 | 312 | 0 | 36.7572 | 36.76 | 11469.12 | 18.37 | 5731.44 | Yes
Technology Consultant - Consultant (GDC India) |  | INT3 | 0 | 160 | 160 | 0 | 0 | 320 | 0 | 36.7572 | 36.76 | 11763.2 | 18.37 | 5878.4 | Yes
Technology Consultant - Consultant (GDC India) |  | INT4 | 0 | 72 | 160 | 0 | 0 | 232 | 0 | 36.7572 | 36.76 | 8528.32 | 18.37 | 4261.84 | Yes

## Travel & Expense
Resource | Speciality | Notes | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | Total | Billable Cost | Non Billable Cost | Billable
MONTH |  |  | 1 | 2 | 3 | 4 | 5
PHASE
MILESTONE |  |  | PO Issue, 15/04/2026, Invoicing, SGD 34750.00 | P1-Design complete, 01/05/2026, Invoicing, SGD 13900.00 | P1- Basic modules complete, 01/06/2026, Invoicing, SGD 27800.00 | P1- Acceptance complete, 01/07/2026, Invoicing, SGD 20850.00 | P2- Acceptance complete, 16/08/2026, Invoicing, SGD 13900.00
|  |  | m1-rev, 30/04/2026, Revenue, SGD 34750.00 | m2-rev, 31/05/2026, Revenue, SGD 13900.00 | m3-rev, 30/06/2026, Revenue, SGD 27800.00 | P2-Integrations complete, 31/07/2026, Invoicing, SGD 27800.00 | m5-rev, 31/08/2026, Revenue, SGD 13900.00
m4-rev, 31/07/2026, Revenue, SGD 48650.00
COST PER PHASE (SGD)
COST PER MONTH (SGD) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Customer Proj/Prgm Mgr - Sr. Consultant (Singapore) |  | Local PM (Joseph) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Info Systems Architect - Sr. Consultant (GDC India) |  | GDC SA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Technology Consultant - Consultant (Singapore) |  | INT1 GDC TC (Trishten) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Technology Consultant - Sr. Consultant (GDC India) |  | SPE1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Technology Consultant - Sr. Consultant (GDC India) |  | SPE2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Technology Consultant - Consultant (GDC India) |  | INT2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Technology Consultant - Consultant (GDC India) |  | INT3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
Technology Consultant - Consultant (GDC India) |  | INT4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes

## Other Costs
Other Cost | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | Total Costs | Total Fees | Billable
MONTH | 1 | 2 | 3 | 4 | 5
PHASE
MILESTONE | PO Issue, 15/04/2026, Invoicing, SGD 34750.00 | P1-Design complete, 01/05/2026, Invoicing, SGD 13900.00 | P1- Basic modules complete, 01/06/2026, Invoicing, SGD 27800.00 | P1- Acceptance complete, 01/07/2026, Invoicing, SGD 20850.00 | P2- Acceptance complete, 16/08/2026, Invoicing, SGD 13900.00
| m1-rev, 30/04/2026, Revenue, SGD 34750.00 | m2-rev, 31/05/2026, Revenue, SGD 13900.00 | m3-rev, 30/06/2026, Revenue, SGD 27800.00 | P2-Integrations complete, 31/07/2026, Invoicing, SGD 27800.00 | m5-rev, 31/08/2026, Revenue, SGD 13900.00
m4-rev, 31/07/2026, Revenue, SGD 48650.00
COST PER PHASE (SGD)
COST PER MONTH (SGD) | 3000 | 3000 | 3000 | 0 | 0 | 9000 | 9000
Risk Cost - Risk Cost | 3000 | 3000 | 3000 | 0 | 0 | 9000 | 9000 | Yes